## Working route
Bb033 CPR101 NJJ | Project Planning |  |  |  |  | Version 1 |  |  |  |  | Version 2 (optional) |  |  |  |  | Version 3 (option) |  |  |  |  | Last Chance Submission
SMART goals ==> | Specific activities | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING (not) DONE DONE LATE HUNG UP | Specific activities | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING (not) DONE DONE LATE HUNG UP | Specific activities | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING (not) DONE DONE LATE HUNG UP | Specific activities | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING (not) DONE DONE LATE HUNG UP | Specific activities | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING (not) DONE DONE LATE HUNG UP
reference and relative due dates |  | PM class date | =====> | 2022-11-23 | Tuesday Nov.22 |  |  | PM class date plus | 9 | days |  |  | PM class date plus | 14 | days |  |  | PM class date plus | -214 | days | Latest possible submission is last day of classes; late penalties apply at 20% per day after your Version 3 due date: | 2022-04-23 | PM class plus | 0 | days
Each group member | Project Mgmt Activity | share with Group |  | Thursday Nov.24 | TO DO
Group Meeting Agenda ==> | create MS Teams Private Channel; for Version 1, create plan with SMART goals and assign tasks | detailed tasks assigned to group members with est. hrs., agreed upon delivery date to Teams, updated Status | 1.5 | Friday Nov.25 | TO DO | review progress, refine plan, update DONE items with actual hours, refine estimates and delivery date/time | In MS Team Channel, select any file you would like reviewed and send a message @instructor to comment on that file. |  | Tuesday Nov.29 | TO DO | Group decision whether to do this version. If so, members plan to complete V2 of their module. | detailed tasks assigned to group members with est. hrs., agreed upon delivery date/time to Teams, updated Status |  | Friday Apr.22 | TO DO | Group decision whether to do this version. If so, members plan to complete V3 of their module. | detailed tasks assigned to group members with est. hrs., agreed upon delivery date/time to Teams, updated Status |  | Wednesday Apr.20 | TO DO | Submit final version of artefacts from Teams to Blackboard. Backup Teams files. | updated DONE items below with actual hours. |  | Wednesday Apr.20 | TO DO
| request review from professor | Group's Team Channel > Files > click ..._Plan.xlsx > click Conversation (top right) > @your_professor "Please review." |  | Saturday Nov.26 |  | request review from professor | Group's Team Channel > Files > click filename > click Conversation (top right) > @your_professor "Please review." |  | Tuesday Nov.29 |  | request review from professor | Group's Team Channel > Files > click filename > click Conversation (top right) > @your_professor "Please review." |  | Sunday Dec.4 |  | request review from professor | Group's Team Channel > Files > click filename > click Conversation (top right) > @your_professor "Please review." |  | Wednesday Apr.20
[Andrea Selina Perez] Fundamentals | Review each other's PM notes on process groups. Agree on how project will be done. Decide which module to do & choose Group Leader |  |  | Friday Nov.25 |  | 1. Rewrite the code; 2. Comment ; 3. Fill up test case until the expected output section; 4. Conduct the test cases; 5. Record result, comments, and test case inputs and outputs in notepad; 6. Upload needed files in MSTeams | 1,2,4. Use VS Code; 3. Download and use excel file for test case; 5. Use excel and notepd | 24 hours | Wednesday Nov.30 | DONE |  |  |  | Monday Dec.5 |  |  |  |  | Thursday Apr.21 |  |  |  |  | Thursday Apr.21
[Yujin Seo] Manipulations | Review each other's PM notes on process groups. Agree on how project will be done. Decide which module to do & choose Group Leader |  |  | Friday Nov.25 |  | 1. created project file with visual studio 2. rewrite the cord in manipulations.c and manipulations.h 3. test module test1. check the module is working test2. using numbers in the inputdata test3. using over length character for string 1 inputdata test4. using over length characters for string 2 inputdata test5. using special characters for input data 4. write the testing module file and module test file 5. upload files on the MT | I uploaded the files with the code rewitten on MS and also upload the test result as an excel and txt file. | 24hrs | Wednesday Nov.30 | DONE |  |  |  | Monday Dec.5 |  |  |  |  | Thursday Apr.21 |  |  |  |  | Thursday Apr.21
[Sean Santoyo] Tokenizing | Review each other's PM notes on process groups. Agree on how project will be done. Decide which module to do & choose Group Leader |  |  | Friday Nov.25 |  |  |  |  | Wednesday Nov.30 |  |  |  |  | Monday Dec.5 |  |  |  |  | Thursday Apr.21 |  |  |  |  | Thursday Apr.21
Shane Conversions Group Leader | Review each other's PM notes on process groups. Agree on how project will be done. Decide which module to do & choose Group Leader |  |  | Saturday Nov.26 |  | REPLACE THIS with your action items and work breakdown structure |  |  | Thursday Dec.1 |  |  |  |  | Tuesday Dec.6 |  |  |  |  | Friday Apr.22 |  |  |  |  | Friday Apr.22
|  |  |  | milestone |  |  |  |  | milestone upload to Blackboard |  |  |  |  | milestone upload to Blackboard |  |  |  |  | DUE DATE upload to Blackboard |  |  |  |  | ABSOLUTE DEADLINE
[7 empty] | What is the group's criteria for acceptance of development (individual files) when promoted to integration (Teams group Files) -- remember the SDLC and Version Control flow? What is definition of done / good enough? Who decides that? | [11 empty] | submissions after this date subject to extra time charge of 20% per day |  |  |  |  | no submissions accepted after this date
Note on A2: Use SMART goals to achieve the Triple Constraint of Cost/Resource vs Time/Schedule vs Scope/Quality.
Note on B2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on C2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on D2: How many hours will the task take?
Note on E2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on F2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: an objective or task according to a Time based target – hours of effort completed by a due date & time DONE: an objective or task Measured as completed HUNG UP: no longer doing something because it became unRealistic. Tell the team right away.
Note on G2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on H2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on I2: How many hours will the task take?
Note on J2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on K2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: an objective or task according to a Time based target – hours of effort completed by a due date & time DONE: an objective or task Measured as completed HUNG UP: no longer doing something because it became unRealistic. Tell the team right away.
Note on L2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on M2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on N2: How many hours will the task take?
Note on O2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on P2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: an objective or task according to a Time based target – hours of effort completed by a due date & time DONE: an objective or task Measured as completed HUNG UP: no longer doing something because it became unRealistic. Tell the team right away.
Note on Q2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on R2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on S2: How many hours will the task take?
Note on T2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on U2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: an objective or task according to a Time based target – hours of effort completed by a due date & time DONE: an objective or task Measured as completed HUNG UP: no longer doing something because it became unRealistic. Tell the team right away.
Note on V2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on W2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on X2: How many hours will the task take?
Note on Y2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on Z2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: an objective or task according to a Time based target – hours of effort completed by a due date & time DONE: an objective or task Measured as completed HUNG UP: no longer doing something because it became unRealistic. Tell the team right away.